## Read me
25-step client onboarding checklist
A practical plan for handoff, kickoff, setup, training, first value, and the 90-day review.
START HERE
1 | Duplicate the checklist before kickoff.
2 | Replace every default role with one accountable person.
3 | Set real dates from the dependencies, not from a generic schedule.
4 | Add the current file, link, instruction, or decision to the Context field.
5 | Update Status and record evidence as the work moves.
Customize before you share
Publish only the rows the client needs to act on, decide, review, or understand. Keep staffing, cost, private risks, and technical delivery detail in the internal system.
FIELD GUIDE
Phase | The onboarding stage that gives the task its place in the sequence.
Timing | The default window. Replace it with real dates that match your work.
Task | A verb plus the specific output or decision.
Default owner | The role accountable for the next move. Replace the role with a person’s name.
Target date | The real date when the next action or decision is due.
Dependency | The input, approval, or prior task that unlocks the work.
Done when | Observable evidence that closes the task.
Visibility | Internal, client-facing, or a shared milestone, decision, or review.
Context | The current file, link, instruction, or decision needed to act.
Status | Not started, In progress, Blocked, or Complete.
Build the client-facing plan in a HummingDeck Room

## Checklist
25-step client onboarding checklist
Replace role defaults with names, set real dates, add working links, and close tasks only when the completion rule is true.
Status options: Not started • In progress • Blocked • Complete
Phase | Timing | Task | Default owner | Target date | Dependency | Done when | Visibility | Context | Status
Internal handoff | Before kickoff | 1. Write down the outcome the client bought | Account executive |  | Signed agreement and sales notes | The handoff states the expected business or operational change in one sentence, using the client’s language. | Internal | Link the CRM or opportunity notes. Reuse the client’s exact wording. | Not started
Internal handoff | Before kickoff | 2. Reconcile the agreement with the sales notes | Account executive |  | Step 1 and the signed agreement | The delivery lead has reviewed the included work, exclusions, dates, services, and material promises made during evaluation. | Internal | Link the signed agreement or order form as the source of truth for commercial terms. | Not started
Internal handoff | Before kickoff | 3. Map the people who can move or stop the work | Account executive |  | Sales notes and known stakeholders | The team can name the executive sponsor, day-to-day lead, technical contact, security or legal contact, and final approver where each role matters. | Internal | Create a stakeholder map. Mark unknown roles instead of guessing. | Not started
Internal handoff | Before kickoff | 4. Put the risks in the open | Implementation lead |  | Steps 2–3 and known delivery constraints | Every known integration, deadline, access issue, staffing gap, and unresolved requirement has a next action and an owner. | Internal | Use an issue log with risk, next action, owner, and target date. | Not started
Internal handoff | Before kickoff | 5. Prepare the shared client home | Customer success or project lead |  | Steps 1–4 and a named delivery lead | The kickoff agenda, current plan, key resources, contacts, and first client actions are available through one link. | Client-facing | Create the Room or shared workspace. Keep private risk and staffing notes internal. | Not started
Client kickoff | Days 1–3 | 6. Send a one-page kickoff brief | Customer success or project lead |  | Step 5 and confirmed participants | The client receives the meeting goal, agenda, participant list, preparation request, and shared workspace at least one working day before the call. | Client-facing | Link the kickoff brief and request only the information needed for the meeting. | Not started
Client kickoff | Days 1–3 | 7. Reconfirm the outcome and the evidence | Customer success lead |  | Step 6 and sponsor participation | The sponsor agrees on the intended result, the evidence that will show progress, and the first review date. | Client-facing | Record the customer result separately from setup milestones. | Not started
Client kickoff | Days 1–3 | 8. Walk through boundaries and change control | Implementation lead |  | Step 2 and the draft delivery plan | The client understands what onboarding covers, what sits outside it, and how either side will raise a scope change. | Client-facing | Point to the agreement and record the agreed change-control path. | Not started
Client kickoff | Days 1–3 | 9. Replace departments with names | Customer success lead |  | Steps 3 and 7–8 | Every workstream has one named owner on the side responsible for the next action, plus a backup where continuity matters. | Client-facing | Update the plan with names. Assign an owner and date for every remaining role gap. | Not started
Client kickoff | Days 1–3 | 10. Choose the communication and escalation path | Customer success lead |  | Step 9 and agreed working channels | Both sides know where routine questions go, where decisions are recorded, how often status is reviewed, and what qualifies as an escalation. | Client-facing | Name one place that owns the decision when email, chat, meetings, and the plan disagree. | Not started
Setup and training | Days 4–14 | 11. Collect the next required inputs | Implementation lead |  | Kickoff decisions and the current setup stage | The brand files, user list, process details, content, or configuration choices needed for the current setup stage have been received and checked. | Client-facing | Request inputs in dependency order. Link the current file, form, or instruction for each request. | Not started
Setup and training | Days 4–14 | 12. Clear security, legal, and access gates | Client technical or security lead |  | Requirements identified in steps 8 and 11 | Required reviews, permissions, domains, accounts, and data-handling decisions are approved or have a dated resolution plan. | Shared milestone | Link the client’s formal approval record. Show only the current gate and next move in the shared plan. | Not started
Setup and training | Days 4–14 | 13. Configure the narrowest useful workflow | Implementation lead |  | Steps 11–12 | The core path works end to end with representative client data or content. | Shared milestone | Link the working setup and note what is deliberately deferred until after first value. | Not started
Setup and training | Days 4–14 | 14. Make the client lead test it | Client project lead |  | Step 13 and client access | The client lead completes the core path, records issues, and approves the setup for training or launch. | Client-facing | Provide the test steps, working link, and one place to record issues and approval. | Not started
Setup and training | Days 4–14 | 15. Split training by role | Enablement or customer success lead |  | Steps 9 and 14 | Each audience has a short agenda and material built around the work it will perform. | Client-facing | Create separate agendas for administrators, daily users, occasional users, and reviewers as needed. | Not started
Setup and training | Days 4–14 | 16. End training with work in the live system | Enablement or customer success lead |  | Step 15 and live access for participants | Required users complete one role-relevant task and can find the recording and reference material afterward. | Client-facing | Reserve time for hands-on work. Link the recording and short reference guide. | Not started
Setup and training | Days 4–14 | 17. Document the support path | Customer success lead |  | Steps 5 and 10 | The client knows the support channel, what context to include, the expected response time, and where to check status. | Client-facing | Keep the support path in the shared client home, not only in an email. | Not started
First value | Days 15–30 | 18. Prepare the first-value run | Customer success lead |  | Steps 7 and 13–17 | The live use case, client participant, required inputs, target date, and acceptable evidence are confirmed. | Client-facing | Use the first-value event defined at kickoff. Link the live work and evidence destination. | Not started
First value | Days 15–30 | 19. Run a real use case | Client project lead |  | Step 18 and live inputs | The client completes the critical path with live work and records where the process slowed down or broke. | Client-facing | Record where the participant had to stop, the cause, and the person taking the next action. | Not started
First value | Days 15–30 | 20. Turn every blocker into a decision | Implementation lead |  | Step 19 and the recorded blocker list | Each launch blocker is fixed, accepted as a known limitation, or moved to a later phase with an owner and date. | Shared decision | Replace “in progress” with the next action, accountable person, and decision date. | Not started
First value | Days 15–30 | 21. Record first value and the remaining gap | Customer success lead |  | Steps 19–20 | Both sides have recorded what happened, the evidence, the gap against the intended result, and the next review date. | Client-facing | Link the evidence. If the event did not happen, record the cause and reset the date explicitly. | Not started
Adoption and review | Days 31–90 | 22. Review adoption by role and workflow | Customer success lead |  | Step 21 and available operational or product data | The review identifies who is using the workflow, who is blocked, and which role needs training, access, or a process change. | Shared review | Use the best available behavior signals. Treat document views as engagement signals, not proof of adoption. | Not started
Adoption and review | Days 31–90 | 23. Give every open item a destination | Implementation lead |  | Step 22 and a full checklist review | Each remaining task is completed, transferred into the ongoing success plan, or removed from scope with the decision recorded. | Shared decision | Record the destination, owner, and date for every open item before the final review. | Not started
Adoption and review | Days 31–90 | 24. Hold the first business review | Customer success lead |  | Steps 7 and 21–23 | The sponsor and working team have reviewed the original goal, evidence, gaps, decisions, and the proposed next-quarter plan. | Client-facing | Send factual updates before the meeting. Use live time for interpretation, tradeoffs, and decisions. | Not started
Adoption and review | Days 31–90 | 25. Document the ongoing operating rhythm | Customer success lead |  | Step 24 and remaining-work decisions | The client has a named relationship owner, support path, review cadence, next priority, and next decision date. | Client-facing | Publish the agreed rhythm in the shared client home and archive setup material that has finished its job. | Not started